SprintPulse

Implementation Guide

Dual-Track Delivery Plan: Custom Connectors vs n8n/Make.com

Version: 2.0.0

Date: June 2026

Classification: Internal / Confidential

# 1. Overview

This guide provides two parallel sprint delivery tracks corresponding to the two architectures in the Technical Architecture document. Track A follows the custom connector approach; Track B uses n8n or Make.com. Both tracks share the same Phase 1 (foundation) and Phase 3 (AI, delivery, polish). Only Phase 2 (the integration layer) differs.

| Phase | Track A (Custom) | Track B (n8n/Make.com) | Weeks |
| --- | --- | --- | --- |
| Phase 1 — Foundation | AWS infra, Auth0, database, CI/CD, Gateway Service skeleton | Identical to Track A | 1–4 (Sprints 1–2) |
| Phase 2 — Integration layer | Custom Connector Service: Jira, GitHub, Slack, Calendar workers | n8n/Make.com flows: 6 workflows configured and tested | 5–8 (Sprints 3–4) |
| Phase 3 — AI + Delivery + Polish | AI Analysis Service, report editor, delivery, archive, beta | Identical to Track A | 9–12 (Sprints 5–6) |
| Total duration | 12 weeks | 12 weeks (same) — but Phase 2 is config not code; lower risk | 12 weeks |
| Engineering effort (Phase 2 only) | ~3 senior engineers × 4 weeks | ~1 engineer × 2 weeks + 1 week QA | Track B ~60% faster |

# 2. Shared Setup — Both Tracks

## 2.1 Repository Structure

| Path | Description | Used In |
| --- | --- | --- |
| apps/web | React / Next.js 14 frontend | Both tracks |
| apps/api-gateway | Express API gateway + tRPC + internal /internal/* endpoints | Both tracks |
| apps/connector-service | Custom sync workers (Bull + OAuth) | Track A only |
| apps/n8n-workflows/ | n8n workflow JSON exports (version-controlled) | Track B only |
| apps/ai-service | FastAPI + LangChain analysis service | Both tracks |
| apps/delivery-service | Slack + Email dispatch | Both tracks |
| packages/shared-types | Zod schemas + TypeScript interfaces | Both tracks |
| packages/db | Drizzle ORM schema + migrations | Both tracks |
| infra/ | Terraform for AWS (ECS, RDS, Redis, ALB, WAF, KMS) | Both tracks |
| infra/n8n/ | Terraform for n8n ECS task + n8n-specific IAM roles | Track B only |

## 2.2 Local Development Setup (Shared)

- Clone repo and install: git clone https://github.com/yourorg/sprintpulse && cd sprintpulse && pnpm install

- Copy env template: cp .env.example .env.local — fill in ANTHROPIC_API_KEY, AUTH0_DOMAIN/CLIENT_ID/SECRET, DATABASE_URL, REDIS_URL

- Start infra: docker compose up -d — spins up Postgres, Redis, LocalStack (AWS emulation)

- Run migrations: pnpm db:migrate

- Seed dev data: pnpm db:seed

- Track A: pnpm dev — starts all services including connector-service

- Track B: pnpm dev:n8n — starts web, api-gateway, ai-service, delivery-service + n8n on localhost:5678

- Access n8n UI at http://localhost:5678 — import workflow JSONs from apps/n8n-workflows/

## 2.3 Internal API Endpoints (Gateway — Both Tracks)

Both architectures use internal sync endpoints on the API Gateway. Track A has the Connector Service calling these. Track B has n8n HTTP Request nodes calling these. The contract is identical.

| Method | Path | Auth | Description |
| --- | --- | --- | --- |
| POST | /internal/sync/jira | X-Internal-API-Key header | Accepts normalised sprint + ticket data; upserts to sprint_data table |
| POST | /internal/sync/github | X-Internal-API-Key header | Accepts PR metrics object; stores in github_metrics table |
| POST | /internal/sync/slack-signals | X-Internal-API-Key header | Accepts array of blocker/risk signals; stores in slack_signals table |
| POST | /internal/sync/calendar | X-Internal-API-Key header | Accepts classified meeting array; stores in calendar_events table |
| POST | /internal/sync/event | X-Internal-API-Key header | Single webhook event (Jira issue or GitHub PR); immediate upsert |
| GET | /internal/workspaces/active | X-Internal-API-Key header | Returns workspaces with integrations enabled (for report generation trigger) |

# 3. Phase 1 — Foundation (Weeks 1–4, Sprints 1–2) — Both Tracks

## Sprint 1 — Infrastructure & Auth

| Deliverable | Owner | Acceptance Criteria |
| --- | --- | --- |
| Terraform: VPC, RDS, Redis, ECS cluster, ALB, WAF, KMS CMK | Platform Eng | terraform apply succeeds; all resources healthy in AWS console |
| GitHub Actions CI/CD pipeline: build → ECR push → ECS deploy | Platform Eng | PR merge to main triggers successful staging deploy within 10 min |
| Auth0 integration: OIDC login, JWT validation, RBAC middleware | Backend Eng | User can log in; JWT validated on API; workspace_admin role gates admin routes |
| Database schema v1: workspaces, users, integrations, reports (empty) | Backend Eng | Migrations run cleanly; seed data loads; drizzle-kit studio shows schema |
| Web app skeleton: login page, empty dashboard, settings nav | Frontend Eng | Authenticated user sees dashboard with 'No data yet' state |

## Sprint 2 — Gateway + Internal API Layer

| Deliverable | Owner | Acceptance Criteria |
| --- | --- | --- |
| Internal /internal/* sync endpoints with X-Internal-API-Key auth | Backend Eng | Postman request with correct API key returns 202; invalid key returns 401 |
| Report generation endpoint: POST /api/reports/generate (queues job) | Backend Eng | Endpoint returns 202 with report_id; job visible in queue (Redis) |
| Webhook ingestion: HMAC verification for Jira + GitHub payloads | Backend Eng | Valid HMAC payload accepted; tampered payload returns 403 |
| Observability: Datadog APM instrumentation on gateway + structured logging | Platform Eng | Traces visible in Datadog; request IDs propagate through services |

# 4. Phase 2 — Integration Layer

TRACK A — Custom Connector Service (Sprints 3–4)

## Sprint 3 (Track A) — Jira + GitHub Connectors

| Deliverable | Details | Acceptance Criteria |
| --- | --- | --- |
| Jira OAuth flow | Atlassian OAuth 2.0 3-legged; token storage encrypted via KMS; scopes: read:jira-work, read:jira-user, offline_access | User completes Jira OAuth; tokens stored; first sync runs within 60s |
| Jira full sync worker | Pull all active sprints + issues; upsert to sprint_data; call /internal/sync/jira | Dashboard shows real Jira sprint data after connect |
| Jira incremental sync | Bull cron job every 15 min; JQL: updated >= -15m; compute burndown % | Ticket status changes reflected in dashboard within 15 min |
| GitHub App setup + OAuth | GitHub App installation token auto-rotation; scopes: contents:read, pull_requests:read | GitHub App installed in test org; token rotation verified |
| GitHub PR sync worker | Fetch PRs updated since last_synced_at; compute avg_review_lag_hours, merge_rate, oldest_open_pr_days | PR metrics visible in dashboard for test repo |
| Jira webhook handler | Register Jira webhooks on connect; HMAC-verified endpoint; process issue_updated + sprint events | Issue status change in Jira reflects in dashboard within 10s |

## Sprint 4 (Track A) — Slack + Calendar + Error Handling

| Deliverable | Details | Acceptance Criteria |
| --- | --- | --- |
| Slack OAuth flow + keyword detection | Slack Bot OAuth; channels:read + channels:history; regex keyword scan: blocked/stuck/waiting on/dependency; deduplicate within 30-min window | Blocker signals from test Slack channel appear in dashboard |
| Google Calendar sync | OAuth 2.0 calendar.readonly; classify events by title keywords (standup/retro/planning/review); 60-min cron | Sprint meeting cadence visible in dashboard |
| Dead-letter queue + alerting | Bull DLQ after 5 retries; Slack alert to #ops-alerts with job type + error | Deliberately failed sync job appears in DLQ; Slack alert fires within 5 min |
| Connector Service unit + integration tests | Vitest; mock Jira/GitHub/Slack APIs; test all normalisation logic; >80% coverage | CI pipeline green; coverage report shows >80% |
| Sync status UI | Dashboard shows last synced time per integration; spinner during active sync; error state with retry button | User can see sync health at a glance; retry works |

TRACK B — n8n / Make.com Workflows (Sprints 3–4)

## Sprint 3 (Track B) — n8n Setup + Jira & GitHub Workflows

| Deliverable | Details | Acceptance Criteria |
| --- | --- | --- |
| n8n ECS deployment (or Make.com account) | Terraform: n8n Fargate task; n8n image pinned; DB connection to existing RDS (n8n_schema); encryption key in Secrets Manager. OR: Make.com team account created, billing configured. | n8n accessible at internal URL; health check green; OR Make.com account active |
| n8n credential configuration | Add Jira OAuth2 API credential; GitHub OAuth2 credential; Google Calendar credential; SprintPulse Internal API Key credential | All credentials show 'Connected' status in n8n credential manager |
| Workflow 1: Jira Sprint Sync | 8-node workflow per spec in Section 3.2; activate with 15-min schedule | Workflow runs successfully; sprint data appears in dashboard via /internal/sync/jira |
| Workflow 2: GitHub PR Sync | 5-node workflow; 15-min schedule; posts to /internal/sync/github | PR metrics appear in dashboard within 15 min of workflow activation |
| Workflow 5: Webhook Handler | Deploy n8n webhook nodes for Jira + GitHub; configure webhook URLs in Jira and GitHub settings | Issue status change in Jira triggers n8n webhook; data updated within 10s |
| n8n workflow JSON export to Git | Export all active workflows as JSON; commit to apps/n8n-workflows/; add to CI check (validate JSON parses) | Workflow definitions version-controlled; CI validates on PR |

## Sprint 4 (Track B) — Slack, Calendar, Error Handling & Report Trigger

| Deliverable | Details | Acceptance Criteria |
| --- | --- | --- |
| n8n Slack credential + Workflow 3 | Add Slack Bot Token credential; deploy 6-node Workflow 3 (blocker detection); 30-min schedule | Blocker signals from monitored Slack channels appear in dashboard |
| Workflow 4: Google Calendar | 4-node workflow; 60-min schedule; event classification code node | Sprint meeting data visible in dashboard |
| Workflow 6: Report Generation Trigger | Weekly schedule + manual HTTP trigger; workspace iteration; SM notification via Slack DM | Report generated automatically on Friday 08:00; SM receives Slack DM |
| Error alerting workflows | Each workflow has error path → Slack alert to #ops-alerts; n8n error workflow configured as global fallback | Deliberately broken workflow (bad API key) triggers Slack alert within 2 min |
| n8n monitoring setup | Expose n8n /metrics endpoint; Datadog agent scrapes; alert on execution failure rate > 5% | Datadog dashboard shows n8n execution counts and error rate |
| Workflow documentation | README in apps/n8n-workflows/ per workflow: purpose, trigger, data contract, how to modify | New engineer can understand and modify a workflow in < 30 min without existing knowledge |

# 5. Phase 3 — AI, Delivery & Polish (Weeks 9–12, Sprints 5–6) — Both Tracks

Phase 3 is identical for both tracks. By this point, normalised data is flowing into PostgreSQL via /internal/sync/* endpoints regardless of which architecture was chosen. The AI service and delivery service are unaware of the difference.

## Sprint 5 — AI Report Generation + Delivery

| Deliverable | Details | Acceptance Criteria |
| --- | --- | --- |
| AI Analysis Service | FastAPI + LangChain; context document assembly; Claude API call with pinned system prompt v1.0; Zod output validation; hallucination check; PII scan | Report draft generated within 90s for a seeded test workspace; all validation checks pass |
| Report editor UI | Inline rich-text editor on draft report; section-by-section editing; track changes visible; Approve & Send button | SM can edit any section of draft; changes saved on blur; Approve triggers delivery |
| Slack delivery | Delivery service: Block Kit report card; collapsible sections; posted to configured channel | Approved report posted to Slack channel within 10s of approval |
| Email delivery | MJML template compiled to HTML; AWS SES dispatch; open tracking via SES click tracking | Approved report delivered to test email; renders correctly in Gmail + Outlook |
| Delivery logs UI | Settings page: delivery history table with status, timestamp, channel, recipient; retry button on failed deliveries | SM can see all past deliveries and retry any failed one |

## Sprint 6 — Beta Hardening + Archive

| Deliverable | Details | Acceptance Criteria |
| --- | --- | --- |
| Report archive | Archive page: searchable by date range, sprint name, status; full report render; PDF export | SM can find and view any past report; PDF export downloads correctly |
| Onboarding flow | Step-by-step connect wizard: Jira → GitHub → Slack → Calendar → generate first report; progress indicators | New user completes onboarding in < 10 min without documentation |
| Error states + empty states | All dashboard widgets have loading, error, and empty states; retry actions where applicable | No blank panels or unhandled errors visible during any user journey |
| Beta user programme | 5 external users (real SMs); feedback collection via in-app widget; weekly sync call | All 5 beta users complete end-to-end flow; CSAT score >= 4.0/5.0 |
| Performance baseline | k6 load test: 500 concurrent report generations; p95 generation time < 90s; delivery service throughput > 200 sends/min | Load test passes without errors; results documented in runbook |

# 6. Track B — n8n Operational Runbook

## 6.1 Common n8n Issues

| Symptom | Likely Cause | Resolution Steps |
| --- | --- | --- |
| Workflow shows 'Error' status in n8n dashboard | API credential expired or revoked; target endpoint unreachable; code node exception | 1. Open workflow execution log in n8n UI. 2. Identify failing node. 3. Check credential status (re-auth if expired). 4. Test HTTP Request node manually with pinned input. 5. Re-activate workflow. |
| Jira data not updating for >30 min | Jira webhook misconfigured OR workflow inactive OR incremental sync cron not running | 1. Check Workflow 1 is Active in n8n. 2. Check Jira webhook config (Settings → Webhooks). 3. Check n8n execution history for recent runs. 4. Manually trigger workflow to test. |
| n8n container restarted; workflows inactive | ECS task replaced (deployment or health check failure); workflows revert to inactive state on new container | 1. SSH to ops or use ECS Exec. 2. Run: curl -X PATCH n8n-api/workflows/{id}/activate for all production workflows. 3. Add to post-deploy script to auto-activate. |
| Make.com: scenario runs out of operations | Monthly operation quota exceeded (especially on free/basic plan) | 1. Check Make.com dashboard → Operations used. 2. Upgrade plan OR reduce polling frequency temporarily. 3. Switch high-frequency scenarios to webhook-only triggers where possible. |
| Slack signals missing from dashboard | Slack Bot token scope removed by admin; monitored channel archived or bot removed | 1. Check Workflow 3 last execution in n8n. 2. Test Slack credential in n8n UI. 3. Re-add bot to channel. 4. Re-authorise Slack OAuth if scope changed. |

## 6.2 Workflow Version Management

- All workflow changes must be made in n8n UI → tested in dev n8n instance first

- After testing: export workflow JSON from n8n (Download button) → commit to apps/n8n-workflows/{workflow-name}.json

- PR review: at least one other engineer reviews the JSON diff for logic changes

- To deploy to production n8n: import JSON via n8n Import feature OR use n8n API: PATCH /api/v1/workflows/{id}

- After import: manually activate workflow; verify first execution succeeds in execution log

- Tag release in Git with workflow version: git tag n8n-v1.2.0 -m 'Add Google Calendar classification'

# 7. Environment Variables — Both Tracks

| Variable | Service | Track | Description |
| --- | --- | --- | --- |
| ANTHROPIC_API_KEY | ai-service | Both | Claude API key — never commit to Git |
| DATABASE_URL | all services | Both | PostgreSQL connection string |
| REDIS_URL | gateway, ai-service, delivery | Both | Redis connection string (smaller instance in Track B) |
| AUTH0_DOMAIN / CLIENT_ID / SECRET | api-gateway | Both | Auth0 tenant credentials |
| INTERNAL_API_KEY | api-gateway | Both | Secret for /internal/* endpoints; shared with Connector Service (A) or n8n (B) |
| AWS_SES_FROM_EMAIL | delivery-service | Both | SES-verified sender address |
| JIRA_CLIENT_ID / SECRET | connector-service | Track A only | Atlassian OAuth app credentials |
| GITHUB_APP_ID / PRIVATE_KEY | connector-service | Track A only | GitHub App credentials |
| SLACK_SIGNING_SECRET | api-gateway | Track A only | Slack webhook HMAC verification |
| N8N_ENCRYPTION_KEY | n8n container | Track B only | AES-256 key for n8n credential vault; stored in Secrets Manager |
| N8N_DB_POSTGRESDB_* | n8n container | Track B only | PostgreSQL connection for n8n state (host, port, db, user, pass) |
| N8N_BASIC_AUTH_USER / PASSWORD | n8n container | Track B only | n8n UI authentication (use strong password; restrict to VPN) |